## Features
Version | Feature | Priority | No of user stories | Planned end date | Status | Percentage completed | Remarks
Basic V1.1 | Brightness control of jewellery | 1 |  |  | WIP
Basic V1.1 | Webcam enable | 1 |  |  | Complete | 90%
Basic V1.1 | Choose File -> Upload a photo | 1 |  |  | WIP | 80%
Basic V1.1 | Fine tune the look and feel | 1 |  |  | WIP
Basic V1.1 | All Deployment options | 1 |  |  | WIP
Basic V1.1 | Photoshop automation | 2 |  |  | Not started
Basic V1.1 | LipStick feature | 2 |  |  | Not started
Basic V1.1 | Compare tried Jewellery photos | 2 |  |  | Not started
Basic V1.1 | Jewellery atributes (price, weight, carrots etc) | 1 |  |  | WIP
Basic V1.1 | Generate tried photos automatically (2nd onwards) | 3 |  |  | Not started
Basic V1.2 | Brightness control of jewellery | 1
Basic V1.2 | Webcam enable | 1
Basic V1.2 | Choose File -> Upload a photo | 1
Basic V1.2 | Fine tune the look and feel | 1
Basic V1.2 | All Deployment options | 1
Basic V1.2 | Photoshop automation | 2
Basic V1.2 | LipStick feature | 2
Basic V1.2 | Compare tried Jewellery photos | 2
Basic V1.2 | Jewellery atributes (price, weight, carrots etc | 1
Basic V1.3 | Brightness control of jewellery | 1
Basic V1.3 | Webcam enable | 1
Basic V1.3 | Choose File -> Upload a photo | 1
Basic V1.3 | Fine tune the look and feel | 1
Basic V1.3 | All Deployment options | 1
Basic V1.3 | Photoshop automation | 2
Basic V1.3 | LipStick feature | 2
Basic V1.3 | Compare tried Jewellery photos | 2
Basic V1.3 | Jewellery atributes (price, weight, carrots etc | 1
Basic V1.1 | Shop Version
Basic V1.2 | E commerce Version
Basic V1.3 | Demo Version

## Miscelleniuos
Points to be discussed
Doubts clarification session (old code)
Engage a guy for photoshopping
Digital marketing
Plan of all the versions
Scheduling standup call ( weekly twice )